## Sprint Plan & Timeline
Sprint | Squad | Module / Workstream | Key Deliverables | Priority | Start Date | End Date | Duration (Weeks) | Dependencies | Status
Sprint 0 | Squad A - Platform / Core | Program Setup & Architecture | Requirement sign-off, wireframes (6 portals), DB schema design, client-owned repo/CI-CD/cloud setup, Jitsi Meet integration architecture (self-hosted vs JaaS), design system. | P0 | 2026-07-13 | 2026-07-26 | 2 | None | In Progress
Sprint 0 | Squad B - Live Classroom & Whiteboard | Live Classroom - Discovery | Jitsi Meet POC (join/host flow, embedding approach via IFrame API / Jitsi SDK), whiteboard library evaluation (build vs open-source lib on top of Jitsi). | P0 | 2026-07-13 | 2026-07-26 | 2 | Program Setup & Architecture | Done
Sprint 0 | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Academic Ops - Discovery | Scheduling engine data model, academic calendar data model, teacher/admission workflow mapping. | P0 | 2026-07-13 | 2026-07-26 | 2 | Program Setup & Architecture | Done
Sprint 0 | Squad D - Parent & Content | Parent & Content - Discovery | Wireframes for admin content flows and parent enrollment/dashboard journeys; enrollment form field list requested from client. | P0 | 2026-07-13 | 2026-07-26 | 2 | Program Setup & Architecture | In Progress
Sprint 0 | Squad E - Billing & Analytics | Billing & Analytics - Discovery | Billing/payout data model, dual payment gateway (Phonics/Maths) account requirements, analytics KPI list finalization. | P0 | 2026-07-13 | 2026-07-26 | 2 | Program Setup & Architecture | In Progress
Sprint 0 | Squad F - QA / DevOps / Release | QA / Release - Discovery | Test strategy & environments, White-label branding requirements gathering, documentation templates, UAT plan skeleton. | P1 | 2026-07-13 | 2026-07-26 | 2 | Program Setup & Architecture | In Progress
Sprint 1 | Squad A - Platform / Core | Common Platform Layer + Admin Auth | Role-based authentication (all 6 roles), RBAC engine, session management, notification scaffolding, base app shell, Admin login/user CRUD, role assignment UI. | P0 | 2026-07-27 | 2026-08-09 | 2 | Program Setup & Architecture | In Progress
Sprint 1 | Squad B - Live Classroom & Whiteboard | Live Classroom Engine (Jitsi Integration) | Jitsi Meet integration: one-click join/host, live video/audio, screen share, chat & reactions, raise hand, mic/video controls, teacher mute/waiting-room controls, class launch from dashboard, long-duration session verification. | P0 | 2026-07-27 | 2026-08-09 | 2 | Live Classroom - Discovery, Common Platform Layer (auth) | In Progress
Sprint 1 | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Scheduling Engine (Core) + Teacher Portal Shell | 1:1 & group scheduling, one-time demo booking, automated scheduling, reschedule/cancel functionality, multi-timezone support, teacher login & session dashboard shell (today/upcoming/completed). | P0 | 2026-07-27 | 2026-08-09 | 2 | Academic Ops - Discovery, Common Platform Layer | In Progress
Sprint 1 | Squad D - Parent & Content | Admin Course/Batch Mgmt + Content Upload | Create/edit/archive batches, course categories & pricing, class duration config, individual/group course setup, course completion tracking & automatic dormant transition, reading book & worksheet upload. | P0 | 2026-07-27 | 2026-08-09 | 2 | Parent & Content - Discovery, Common Platform Layer | Done
Sprint 1 | Squad E - Billing & Analytics | Billing Core + Dual Payment Gateway | Packages & subscription setup, session-based & recurring charging, auto invoice/receipt generation, dual payment gateway integration (Phonics/Maths accounts). | P0 | 2026-07-27 | 2026-08-09 | 2 | Billing & Analytics - Discovery, Common Platform Layer | In Progress
Sprint 1 | Squad F - QA / DevOps / Release | Test Automation Setup | CI pipeline test integration, smoke-test suite for Sprint 1 deliverables, security test plan. | P1 | 2026-07-27 | 2026-08-09 | 2 | QA / Release - Discovery | Done
Sprint 2 | Squad A - Platform / Core | Sub Admin Portal + Audit | Sub-admin login, module-wise access assignment, feature-level permission control, role-wise dashboard visibility, access boundaries, audit trail for sub-admin/admin actions, plus a named 'Academic Coordinator' permission preset (reschedule, availability check, holiday/leave view). | P0 | 2026-08-10 | 2026-08-23 | 2 | Common Platform Layer + Admin Auth | Not Started
Sprint 2 | Squad B - Live Classroom & Whiteboard | Interactive Whiteboard System | Infinite/multi-page board, drawing tools/shapes/text, sticky annotations, teacher-controlled interaction permissions layered on top of the Jitsi session. | P0 | 2026-08-10 | 2026-08-23 | 2 | Live Classroom Engine (Jitsi Integration) | Not Started
Sprint 2 | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Academic Calendar + Teacher Attendance/Leave | Centralized colour-coded academic calendar (Admin/Coordinator/Teacher views), scheduling conflict/availability check, holiday & teacher leave calendar, reminders/no-show/delay alerts, teacher attendance capture, leave application (6-hour rule) & admin approval workflow. | P0 | 2026-08-10 | 2026-08-23 | 2 | Scheduling Engine (Core) + Teacher Portal Shell | Not Started
Sprint 2 | Squad D - Parent & Content | Content Access Control + Parent Enrollment | Download permission control, parent dashboard visibility toggle, recording access control (15-day expiry), parent login, mandatory first-login child enrollment form, multi-child dashboard, admin form approval workflow. | P0 | 2026-08-10 | 2026-08-23 | 2 | Admin Course/Batch Mgmt + Content Upload | Not Started
Sprint 2 | Squad E - Billing & Analytics | Department-wise Transactions + Fee Suspension | Department-wise transaction recording & centralized dashboard, fee overdue check automation, account suspension logic, Pay Now popup + access restoration, refund tracking workflow, renewal tracking workflow. | P0 | 2026-08-10 | 2026-08-23 | 2 | Billing Core + Dual Payment Gateway | Not Started
Sprint 2 | Squad F - QA / DevOps / Release | Continuous Regression - Wave 1 | Regression pass on Auth/RBAC, Admin core, Jitsi integration; security testing kick-off (RBAC & payment data access). | P0 | 2026-08-10 | 2026-08-23 | 2 | Sprint 1 deliverables across all squads | Not Started
Sprint 3 | Squad A - Platform / Core | Admin Dashboard & KPIs | Total/active students, revenue & enrollment widgets, conversion/renewal/refund widgets, teacher utilization, active vs dormant batch view, course-wise revenue widget, plus a named read-only 'Management' executive-dashboard role. | P1 | 2026-08-24 | 2026-09-06 | 2 | Sub Admin Portal + Audit | Not Started
Sprint 3 | Squad B - Live Classroom & Whiteboard | Gamification Layer (Part 1) + Interactive Activities | Drag & drop, tag & match, hotspot click, select-correct-answer whiteboard activities; live quizzes & instant scoring; leaderboards, milestones, stars, badges. | P0 | 2026-08-24 | 2026-09-06 | 2 | Interactive Whiteboard System | Not Started
Sprint 3 | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Teacher Demo Feedback + Admission Team Portal | Mandatory demo feedback form (academic level, strengths, recommended course, batch type), Admission team login/dashboard, flexible demo scheduling (multi-parent invite) with auto teacher assignment, demo status tracking, feedback review, parent/enrollment tracking. | P0 | 2026-08-24 | 2026-09-06 | 2 | Academic Calendar + Teacher Attendance/Leave | Not Started
Sprint 3 | Squad D - Parent & Content | Parent Resources, Payments & Notifications | Schedule view & join live class, worksheet/book/recording access, invoice/receipt view & payment history, Pay Now + fee suspension redirect, notifications & automated reports. | P0 | 2026-08-24 | 2026-09-06 | 2 | Content Access Control + Parent Enrollment | Not Started
Sprint 3 | Squad E - Billing & Analytics | Teacher Payout Engine | Auto payout calculation post-class, payout visibility rules (admin sees all, teacher sees own), configurable payout rates, monthly payout cycle with history and email dispatch, student/teacher no-show handling with independent carried-forward session logic. | P0 | 2026-08-24 | 2026-09-06 | 2 | Department-wise Transactions + Fee Suspension | Not Started
Sprint 3 | Squad F - QA / DevOps / Release | Continuous Regression - Wave 2 + Load Test Prep | Regression on Whiteboard, Scheduling, Teacher/Admission portals; live-classroom concurrency load-test scripting begins. | P0 | 2026-08-24 | 2026-09-06 | 2 | Sprint 2 deliverables across all squads | Not Started
Sprint 4 | Squad A - Platform / Core | White-Label Branding + Integrations | Custom branding, own domain configuration, website/app embed, CRM integration, calendar sync, email/SMS reminder integration finalization. | P1 | 2026-09-07 | 2026-09-20 | 2 | Admin Dashboard & KPIs | Not Started
Sprint 4 | Squad B - Live Classroom & Whiteboard | Gamification Layer (Part 2) + Engagement Tracking | Celebration animations, birthday/dhol/clapping effects, student engagement tracking (participation, click activity, quiz attempts, whiteboard interaction, attention signals, engagement scores, learning outcome indicators). | P1 | 2026-09-07 | 2026-09-20 | 2 | Gamification Layer (Part 1) + Interactive Activities | Not Started
Sprint 4 | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Admission Reporting + Teacher Performance | Centralized admission reporting (demo/payment/enrollment/conversion), transaction history & receipt visibility, teacher performance view (tutor notes, session/attendance reports). | P1 | 2026-09-07 | 2026-09-20 | 2 | Teacher Demo Feedback + Admission Team Portal | Not Started
Sprint 4 | Squad D - Parent & Content | Parent Notifications Hardening | Finalize session reminders, attendance updates, performance summaries, payment reminders, automated report generation; multi-child dashboard polish. | P1 | 2026-09-07 | 2026-09-20 | 2 | Parent Resources, Payments & Notifications | Not Started
Sprint 4 | Squad E - Billing & Analytics | Analytics, AI Reports & BI Dashboard | Student analytics (attendance/participation/quiz/whiteboard/engagement), AI performance reports (talk-time, camera attentiveness), Admin BI dashboard, CSV exports, bulk email. | P1 | 2026-09-07 | 2026-09-20 | 2 | Teacher Payout Engine | Not Started
Sprint 4 | Squad F - QA / DevOps / Release | Continuous Regression - Wave 3 | Regression on Billing/Payout/Analytics; begin full technical & API documentation drafting. | P0 | 2026-09-07 | 2026-09-20 | 2 | Sprint 3 deliverables across all squads | Not Started
Sprint 5 | A/B/C/D/E | Cross-Squad Integration Hardening | End-to-end integration pass across all portals and the Jitsi-powered live classroom; fix cross-module defects surfaced by Squad F regression; finalize documentation, admin guide, source code/repo/cloud/API ownership transfer packaging. | P0 | 2026-09-21 | 2026-10-04 | 2 | All Sprint 0-4 deliverables | Not Started
Sprint 5 | Squad F - QA / DevOps / Release | Full Regression + Load + Security Testing | Full end-to-end regression across all 6 portals, live-classroom concurrency load testing, security testing (RBAC, payment data, session access), bug triage. | P0 | 2026-09-21 | 2026-10-04 | 2 | All squads' Sprint 4 deliverables | Not Started
Stabilization Week | Squad F - QA / DevOps / Release | UAT, Deployment & Go-Live | Operational readiness sign-off, client UAT, final bug fixes, production deployment, admin training, go-live, hypercare kickoff (hypercare continues beyond the 3-month build window). | P0 | 2026-10-05 | 2026-10-11 | 1 | Cross-Squad Integration Hardening, Full Regression | Not Started

## Task Backlog (All Modules)
Module | Squad | Task | Priority | Est. Effort (Days) | Owner | Sprint | Start Date | End Date | Status
Program Setup & Architecture | Squad A - Platform / Core | Requirement walkthrough & sign-off with stakeholders | P0 | 2 | PM/BA | Sprint 0 | 2026-07-13 | 2026-07-26 | Blocked
Program Setup & Architecture | Squad A - Platform / Core | UX wireframes for all 6 portals (Admin, Sub Admin, Admission, Teacher, Parent, Student) | P0 | 5 | Frontend | Sprint 0 | 2026-07-13 | 2026-07-26 | Done
Program Setup & Architecture | Squad A - Platform / Core | Tech stack finalization (web framework, database, hosting) | P0 | 2 | Full-Stack | Sprint 0 | 2026-07-13 | 2026-07-26 | Done
Program Setup & Architecture | Squad A - Platform / Core | Jitsi Meet integration architecture (self-hosted vs JaaS, embedding approach) | P0 | 3 | Backend | Sprint 0 | 2026-07-13 | 2026-07-26 | Done
Program Setup & Architecture | Squad A - Platform / Core | Database schema design (white-label / multi-tenant ready) | P0 | 4 | Backend | Sprint 0 | 2026-07-13 | 2026-07-26 | Done
Program Setup & Architecture | Squad A - Platform / Core | Git repository setup under client-owned account | P0 | 1 | DevOps | Sprint 0 | 2026-07-13 | 2026-07-26 | Blocked
Program Setup & Architecture | Squad A - Platform / Core | CI/CD pipeline setup | P0 | 2 | DevOps | Sprint 0 | 2026-07-13 | 2026-07-26 | Done
Program Setup & Architecture | Squad A - Platform / Core | Cloud infrastructure provisioning (client-owned account) | P0 | 2 | DevOps | Sprint 0 | 2026-07-13 | 2026-07-26 | Blocked
Program Setup & Architecture | Squad A - Platform / Core | Design system / component library setup | P1 | 3 | Frontend | Sprint 0 | 2026-07-13 | 2026-07-26 | Done
Common Platform Layer + Admin Auth | Squad A - Platform / Core | Role-based authentication framework (all 6 roles) | P0 | 5 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Common Platform Layer + Admin Auth | Squad A - Platform / Core | RBAC engine & permission matrix | P0 | 4 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Common Platform Layer + Admin Auth | Squad A - Platform / Core | Session management & secure token handling | P0 | 2 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Common Platform Layer + Admin Auth | Squad A - Platform / Core | Notification service scaffolding (email/SMS) | P0 | 3 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Common Platform Layer + Admin Auth | Squad A - Platform / Core | Base application shell & navigation per portal | P0 | 4 | Frontend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Common Platform Layer + Admin Auth | Squad A - Platform / Core | Audit logging framework | P1 | 2 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Common Platform Layer + Admin Auth | Squad A - Platform / Core | Admin login/logout & secure access | P0 | 1 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Common Platform Layer + Admin Auth | Squad A - Platform / Core | Parent/Student/Teacher/Admission/SubAdmin user CRUD | P0 | 4 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Common Platform Layer + Admin Auth | Squad A - Platform / Core | Role assignment & permission control UI | P0 | 3 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | In Progress
Common Platform Layer + Admin Auth | Squad A - Platform / Core | User status management (active/suspended) | P0 | 1 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Common Platform Layer + Admin Auth | Squad A - Platform / Core | Auto-send login credentials email on user account creation (parent receives credentials on admin-created account) | P0 | 1 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Frontend-Backend API Integration | Squad A - Platform / Core | Frontend API client layer (fetch wrapper, JWT storage, typed endpoints, VITE_API_BASE_URL env config) | P0 | 1 | Frontend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Frontend-Backend API Integration | Squad A - Platform / Core | Auth integration: real login/logout against /api/auth, token persistence, role-based redirect | P0 | 2 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Frontend-Backend API Integration | Squad A - Platform / Core | CORS & environment configuration (dev/prod API base URLs, allowed origins) | P0 | 1 | DevOps | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Frontend-Backend API Integration | Squad A - Platform / Core | Wire Admin user management screens to Users API (list/create/status) | P0 | 2 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Frontend-Backend API Integration | Squad A - Platform / Core | Wire Admin course/batch screens to Courses & Batches APIs | P0 | 2 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | In Progress
Frontend-Backend API Integration | Squad A - Platform / Core | API error/loading/empty-state handling pattern for wired pages (progressive mock-data replacement per sprint) | P1 | 1 | Frontend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Sub Admin Portal + Audit | Squad A - Platform / Core | Sub-admin login & secure access | P0 | 1 | Full-Stack | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Sub Admin Portal + Audit | Squad A - Platform / Core | Module-wise access assignment UI | P0 | 3 | Full-Stack | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Sub Admin Portal + Audit | Squad A - Platform / Core | Feature-level permission control (view/add/edit/delete) | P0 | 3 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Sub Admin Portal + Audit | Squad A - Platform / Core | Role-wise dashboard visibility | P1 | 2 | Frontend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Sub Admin Portal + Audit | Squad A - Platform / Core | Access boundary enforcement (no full access by default) | P0 | 1 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Sub Admin Portal + Audit | Squad A - Platform / Core | Audit trail for sub-admin actions | P1 | 2 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Sub Admin Portal + Audit | Squad A - Platform / Core | Configure 'Academic Coordinator' role (scheduling/calendar-scoped Sub Admin preset: reschedule, availability check, holiday/leave visibility) | P1 | 2 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Admin Dashboard & KPIs | Squad A - Platform / Core | Dashboard shell: total/active students, revenue, enrollments | P1 | 3 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Admin Dashboard & KPIs | Squad A - Platform / Core | Conversion & renewal rate widgets | P1 | 2 | Frontend | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Admin Dashboard & KPIs | Squad A - Platform / Core | Teacher utilization & attendance widgets | P1 | 2 | Frontend | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Admin Dashboard & KPIs | Squad A - Platform / Core | Refund rate & batch occupancy widgets | P1 | 2 | Frontend | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Admin Dashboard & KPIs | Squad A - Platform / Core | Course-wise revenue widget | P1 | 1 | Frontend | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Admin Dashboard & KPIs | Squad A - Platform / Core | Active batches vs dormant batches view | P0 | 2 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Admin Dashboard & KPIs | Squad A - Platform / Core | Configure 'Management' read-only executive dashboard role (Sub Admin preset scoped to KPI view only) | P1 | 1 | Backend | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
White-Label Branding + Integrations | Squad A - Platform / Core | Custom branding (logo, colours, naming) | P1 | 2 | Frontend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
White-Label Branding + Integrations | Squad A - Platform / Core | Own domain configuration | P1 | 1 | DevOps | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
White-Label Branding + Integrations | Squad A - Platform / Core | Website/app embed integration | P1 | 3 | Full-Stack | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
White-Label Branding + Integrations | Squad A - Platform / Core | CRM integration | P2 | 3 | Backend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
White-Label Branding + Integrations | Squad A - Platform / Core | Calendar sync integration | P1 | 2 | Backend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
White-Label Branding + Integrations | Squad A - Platform / Core | Email/SMS reminder integration finalization | P1 | 2 | Backend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Live Classroom - Discovery | Squad B - Live Classroom & Whiteboard | Jitsi Meet POC (join/host flow via IFrame API / SDK) | P0 | 3 | Backend | Sprint 0 | 2026-07-13 | 2026-07-26 | Done
Live Classroom - Discovery | Squad B - Live Classroom & Whiteboard | Whiteboard library evaluation (open-source lib vs custom build) | P0 | 2 | Frontend | Sprint 0 | 2026-07-13 | 2026-07-26 | Done
Live Classroom Engine (Jitsi Integration) | Squad B - Live Classroom & Whiteboard | Jitsi Meet integration: one-click join/host, live video/audio | P0 | 5 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Live Classroom Engine (Jitsi Integration) | Squad B - Live Classroom & Whiteboard | Screen sharing (native Jitsi feature wiring) | P0 | 1 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Live Classroom Engine (Jitsi Integration) | Squad B - Live Classroom & Whiteboard | Chat & reactions (Jitsi native + custom UI wrapper) | P0 | 2 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Live Classroom Engine (Jitsi Integration) | Squad B - Live Classroom & Whiteboard | Raise hand | P0 | 1 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Live Classroom Engine (Jitsi Integration) | Squad B - Live Classroom & Whiteboard | Mic/video participation controls | P0 | 2 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Live Classroom Engine (Jitsi Integration) | Squad B - Live Classroom & Whiteboard | Class launch controls (start from teacher dashboard) | P0 | 2 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Live Classroom Engine (Jitsi Integration) | Squad B - Live Classroom & Whiteboard | Teacher controls: mute/unmute, video permission, waiting room | P0 | 3 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | In Progress
Live Classroom Engine (Jitsi Integration) | Squad B - Live Classroom & Whiteboard | Auto session recording (Jitsi recording + cloud storage wiring) | P0 | 3 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | Blocked
Live Classroom Engine (Jitsi Integration) | Squad B - Live Classroom & Whiteboard | Session summaries & history | P1 | 2 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Not Started
Live Classroom Engine (Jitsi Integration) | Squad B - Live Classroom & Whiteboard | Long-duration session support & cloud storage cost/stability verification | P1 | 2 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | Blocked
Interactive Whiteboard System | Squad B - Live Classroom & Whiteboard | Infinite whiteboard canvas | P0 | 4 | Full-Stack | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Interactive Whiteboard System | Squad B - Live Classroom & Whiteboard | Multi-page board | P0 | 3 | Full-Stack | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Interactive Whiteboard System | Squad B - Live Classroom & Whiteboard | Drawing tools, shapes, text tools | P0 | 4 | Full-Stack | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Interactive Whiteboard System | Squad B - Live Classroom & Whiteboard | Sticky annotations | P1 | 1 | Frontend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Interactive Whiteboard System | Squad B - Live Classroom & Whiteboard | Teacher-controlled interaction permissions | P0 | 3 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Interactive Whiteboard System | Squad B - Live Classroom & Whiteboard | Remote access grant control (teacher gives a student board/screen control) | P2 | 1 | Full-Stack | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Gamification Layer (Part 1) + Interactive Activities | Squad B - Live Classroom & Whiteboard | Drag & drop activities | P0 | 3 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Gamification Layer (Part 1) + Interactive Activities | Squad B - Live Classroom & Whiteboard | Tag & match activities | P0 | 3 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Gamification Layer (Part 1) + Interactive Activities | Squad B - Live Classroom & Whiteboard | Hotspot click activities | P0 | 2 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Gamification Layer (Part 1) + Interactive Activities | Squad B - Live Classroom & Whiteboard | Select-correct-answer-on-board interaction | P0 | 2 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Gamification Layer (Part 1) + Interactive Activities | Squad B - Live Classroom & Whiteboard | Live quizzes & instant scoring | P0 | 4 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Gamification Layer (Part 1) + Interactive Activities | Squad B - Live Classroom & Whiteboard | Leaderboards | P0 | 2 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Gamification Layer (Part 1) + Interactive Activities | Squad B - Live Classroom & Whiteboard | Milestones, stars, badges | P0 | 3 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Gamification Layer (Part 2) + Engagement Tracking | Squad B - Live Classroom & Whiteboard | Celebration animations (reward moments) | P1 | 2 | Frontend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Gamification Layer (Part 2) + Engagement Tracking | Squad B - Live Classroom & Whiteboard | Birthday celebration feature | P2 | 1 | Frontend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Gamification Layer (Part 2) + Engagement Tracking | Squad B - Live Classroom & Whiteboard | Dhol / clapping sound effects for recognition | P2 | 1 | Frontend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Gamification Layer (Part 2) + Engagement Tracking | Squad B - Live Classroom & Whiteboard | Student engagement tracking: participation, click activity, quiz attempts | P1 | 3 | Backend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Gamification Layer (Part 2) + Engagement Tracking | Squad B - Live Classroom & Whiteboard | Whiteboard interaction & attention signal tracking | P1 | 3 | Backend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Gamification Layer (Part 2) + Engagement Tracking | Squad B - Live Classroom & Whiteboard | Engagement score & learning outcome indicators | P1 | 3 | Backend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Academic Ops - Discovery | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Scheduling engine data model | P0 | 2 | Backend | Sprint 0 | 2026-07-13 | 2026-07-26 | Done
Academic Ops - Discovery | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Academic calendar data model | P0 | 2 | Backend | Sprint 0 | 2026-07-13 | 2026-07-26 | Done
Academic Ops - Discovery | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Teacher/admission workflow mapping | P0 | 2 | PM/BA | Sprint 0 | 2026-07-13 | 2026-07-26 | Done
Scheduling Engine (Core) + Teacher Portal Shell | Squad C - Academic Ops (Scheduling/Teacher/Admission) | 1:1 class scheduling | P0 | 3 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Scheduling Engine (Core) + Teacher Portal Shell | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Group class scheduling | P0 | 3 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Scheduling Engine (Core) + Teacher Portal Shell | Squad C - Academic Ops (Scheduling/Teacher/Admission) | One-time demo booking (parent / admission-initiated) | P0 | 3 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | In Progress
Scheduling Engine (Core) + Teacher Portal Shell | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Automated scheduling logic | P0 | 3 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Scheduling Engine (Core) + Teacher Portal Shell | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Reschedule / cancel session functionality | P0 | 2 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Scheduling Engine (Core) + Teacher Portal Shell | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Multi-timezone support | P0 | 2 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | In Progress
Scheduling Engine (Core) + Teacher Portal Shell | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Teacher login/logout & dashboard (today/upcoming/completed sessions) | P0 | 3 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | In Progress
Scheduling Engine (Core) + Teacher Portal Shell | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Teacher session resource upload (share uploaded class resources into the live session) | P1 | 2 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | In Progress
Academic Calendar + Teacher Attendance/Leave | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Centralized colour-coded academic calendar (Admin/Coordinator/Teacher views) | P0 | 4 | Full-Stack | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Academic Calendar + Teacher Attendance/Leave | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Status colour coding (scheduled/completed/cancelled/no-show/demo/rescheduled/holiday/leave) | P0 | 2 | Frontend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Academic Calendar + Teacher Attendance/Leave | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Scheduling conflict / teacher availability check (prevent double-booking across batches) | P0 | 3 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Academic Calendar + Teacher Attendance/Leave | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Holiday calendar management | P1 | 1 | Full-Stack | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Academic Calendar + Teacher Attendance/Leave | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Teacher leave calendar integration | P0 | 2 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Academic Calendar + Teacher Attendance/Leave | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Booking confirmation emails | P0 | 1 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Academic Calendar + Teacher Attendance/Leave | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Email reminders, no-show alerts, delayed session alerts | P0 | 3 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Academic Calendar + Teacher Attendance/Leave | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Student attendance capture | P0 | 2 | Full-Stack | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Academic Calendar + Teacher Attendance/Leave | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Session attendance & recording linkage | P0 | 2 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Academic Calendar + Teacher Attendance/Leave | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Leave application module (6-hour restriction rule, auto-block, notification) | P0 | 3 | Full-Stack | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Academic Calendar + Teacher Attendance/Leave | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Leave history & status view + admin approval/rejection workflow | P0 | 3 | Full-Stack | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Academic Calendar + Teacher Attendance/Leave | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Teacher attendance capture (login/join-based) | P0 | 1 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Teacher Demo Feedback + Admission Team Portal | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Mandatory demo feedback form (academic level, strengths, recommended course, batch type) | P0 | 3 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Teacher Demo Feedback + Admission Team Portal | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Admission team login & dashboard | P0 | 2 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Teacher Demo Feedback + Admission Team Portal | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Demo booking overview & conversion status summary | P0 | 2 | Frontend | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Teacher Demo Feedback + Admission Team Portal | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Schedule demo class (one-time, flexible multi-parent invite) | P0 | 3 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Teacher Demo Feedback + Admission Team Portal | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Auto-assign teacher to demo session | P1 | 2 | Backend | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Teacher Demo Feedback + Admission Team Portal | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Demo status tracking | P0 | 1 | Backend | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Teacher Demo Feedback + Admission Team Portal | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Demo feedback review (from teacher submissions) | P0 | 2 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Teacher Demo Feedback + Admission Team Portal | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Parent details & contact record management | P0 | 2 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Teacher Demo Feedback + Admission Team Portal | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Payment link sharing & payment status (pending/paid/partial) | P0 | 2 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Teacher Demo Feedback + Admission Team Portal | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Conversion pipeline (Demo Completed/Follow-up/Enrolled/Not Interested) | P0 | 2 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Teacher Demo Feedback + Admission Team Portal | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Tutor notes creation & management (teacher-side entry per student/session) | P1 | 1 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Admission Reporting + Teacher Performance | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Centralized reporting (demo/payment/enrollment/conversion reports) | P1 | 2 | Backend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Admission Reporting + Teacher Performance | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Transaction history & receipt visibility | P1 | 1 | Frontend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Admission Reporting + Teacher Performance | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Teacher performance view (tutor notes, session/attendance reports) | P1 | 2 | Frontend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Admission Reporting + Teacher Performance | Squad C - Academic Ops (Scheduling/Teacher/Admission) | Session summary & class history view | P1 | 2 | Frontend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Parent & Content - Discovery | Squad D - Parent & Content | Wireframes for admin content flows and parent enrollment/dashboard journeys | P0 | 3 | Frontend | Sprint 0 | 2026-07-13 | 2026-07-26 | Done
Parent & Content - Discovery | Squad D - Parent & Content | Enrollment form field list requested from client (blocking dependency) | P0 | 1 | PM/BA | Sprint 0 | 2026-07-13 | 2026-07-26 | Blocked
Admin Course/Batch Mgmt + Content Upload | Squad D - Parent & Content | Create/edit/archive batches | P0 | 3 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Admin Course/Batch Mgmt + Content Upload | Squad D - Parent & Content | Course categories & pricing setup | P0 | 2 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Admin Course/Batch Mgmt + Content Upload | Squad D - Parent & Content | Class duration configuration (30/45/60 min) | P0 | 1 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Admin Course/Batch Mgmt + Content Upload | Squad D - Parent & Content | Individual & group course setup | P0 | 2 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Admin Course/Batch Mgmt + Content Upload | Squad D - Parent & Content | Batch capacity & teacher assignment | P0 | 2 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Admin Course/Batch Mgmt + Content Upload | Squad D - Parent & Content | Active vs dormant batch lifecycle logic | P0 | 2 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Admin Course/Batch Mgmt + Content Upload | Squad D - Parent & Content | Course completion tracking (auto-detect when all sessions in a batch are done) | P0 | 2 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Admin Course/Batch Mgmt + Content Upload | Squad D - Parent & Content | Automatic batch-to-dormant transition after course completion | P0 | 2 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Admin Course/Batch Mgmt + Content Upload | Squad D - Parent & Content | Reading book upload & library management | P0 | 2 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Admin Course/Batch Mgmt + Content Upload | Squad D - Parent & Content | Worksheet upload & download permission control | P0 | 2 | Full-Stack | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Content Access Control + Parent Enrollment | Squad D - Parent & Content | Resource management (tagging, categorization) | P1 | 2 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Content Access Control + Parent Enrollment | Squad D - Parent & Content | Parent dashboard content visibility toggle (admin-controlled) | P0 | 2 | Full-Stack | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Content Access Control + Parent Enrollment | Squad D - Parent & Content | Recording access control (15-day view window + auto-expiry job) | P0 | 3 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Content Access Control + Parent Enrollment | Squad D - Parent & Content | Parent login/logout | P0 | 1 | Full-Stack | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Content Access Control + Parent Enrollment | Squad D - Parent & Content | Mandatory first-login child enrollment form | P0 | 4 | Full-Stack | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Content Access Control + Parent Enrollment | Squad D - Parent & Content | Multiple children under one account (single unified dashboard) | P0 | 3 | Full-Stack | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Content Access Control + Parent Enrollment | Squad D - Parent & Content | Enrollment status view | P0 | 1 | Frontend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Content Access Control + Parent Enrollment | Squad D - Parent & Content | Admin view/edit/approve/download of submitted forms | P0 | 2 | Full-Stack | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Parent Resources, Payments & Notifications | Squad D - Parent & Content | Dashboard: classes completed/remaining, attendance %, fee status, learning timeline | P0 | 3 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Parent Resources, Payments & Notifications | Squad D - Parent & Content | Schedule view & join live class | P0 | 2 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Parent Resources, Payments & Notifications | Squad D - Parent & Content | Reading book & worksheet access (download, admin-gated visibility) | P0 | 2 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Parent Resources, Payments & Notifications | Squad D - Parent & Content | Recording view-only access (15-day window, auto-remove after expiry) | P0 | 2 | Backend | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Parent Resources, Payments & Notifications | Squad D - Parent & Content | Invoice/receipt view & payment history | P0 | 2 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Parent Resources, Payments & Notifications | Squad D - Parent & Content | Pay Now access & fee suspension popup redirect | P0 | 3 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Parent Notifications Hardening | Squad D - Parent & Content | Notifications: session reminders, attendance updates | P1 | 2 | Backend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Parent Notifications Hardening | Squad D - Parent & Content | Performance summaries & payment reminders | P1 | 2 | Backend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Parent Notifications Hardening | Squad D - Parent & Content | Automated reports generation | P1 | 2 | Backend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Parent Notifications Hardening | Squad D - Parent & Content | Multi-child dashboard polish & edge cases | P1 | 2 | Full-Stack | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Billing & Analytics - Discovery | Squad E - Billing & Analytics | Billing/payout data model | P0 | 2 | Backend | Sprint 0 | 2026-07-13 | 2026-07-26 | Done
Billing & Analytics - Discovery | Squad E - Billing & Analytics | Dual payment gateway (Phonics/Maths) account requirements | P0 | 1 | PM/BA | Sprint 0 | 2026-07-13 | 2026-07-26 | Blocked
Billing & Analytics - Discovery | Squad E - Billing & Analytics | Analytics KPI list finalization | P0 | 1 | PM/BA | Sprint 0 | 2026-07-13 | 2026-07-26 | Done
Billing Core + Dual Payment Gateway | Squad E - Billing & Analytics | Package & subscription plan setup | P0 | 3 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Billing Core + Dual Payment Gateway | Squad E - Billing & Analytics | Session-based charging | P0 | 2 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Billing Core + Dual Payment Gateway | Squad E - Billing & Analytics | Recurring payments & auto billing | P0 | 3 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | In Progress
Billing Core + Dual Payment Gateway | Squad E - Billing & Analytics | Auto invoice & receipt generation | P0 | 3 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Billing Core + Dual Payment Gateway | Squad E - Billing & Analytics | Dual payment gateway integration (Phonics account + Maths account) | P0 | 5 | Backend | Sprint 1 | 2026-07-27 | 2026-08-09 | In Progress
Department-wise Transactions + Fee Suspension | Squad E - Billing & Analytics | Department-wise transaction recording & centralized dashboard | P0 | 3 | Full-Stack | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Department-wise Transactions + Fee Suspension | Squad E - Billing & Analytics | Admin assignment of parent/student to correct payment account | P0 | 1 | Full-Stack | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Department-wise Transactions + Fee Suspension | Squad E - Billing & Analytics | Fee overdue check automation | P0 | 2 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Department-wise Transactions + Fee Suspension | Squad E - Billing & Analytics | Account suspension logic (block session/content access) | P0 | 2 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Department-wise Transactions + Fee Suspension | Squad E - Billing & Analytics | Pending-fee popup with Pay Now redirect | P0 | 1 | Frontend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Department-wise Transactions + Fee Suspension | Squad E - Billing & Analytics | Access restoration (auto on payment / admin approval) | P0 | 2 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Department-wise Transactions + Fee Suspension | Squad E - Billing & Analytics | Admin notification on payment received | P1 | 1 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Department-wise Transactions + Fee Suspension | Squad E - Billing & Analytics | Refund request & fee tracking workflow | P1 | 3 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Department-wise Transactions + Fee Suspension | Squad E - Billing & Analytics | Renewal tracking workflow (batch/course renewal conversion) | P1 | 2 | Backend | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Teacher Payout Engine | Squad E - Billing & Analytics | Auto payout calculation post-class | P0 | 4 | Backend | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Teacher Payout Engine | Squad E - Billing & Analytics | Payout visibility rules (admin sees all, teacher sees own) | P0 | 1 | Backend | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Teacher Payout Engine | Squad E - Billing & Analytics | Configurable payout rates by batch duration/teacher | P0 | 2 | Full-Stack | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Teacher Payout Engine | Squad E - Billing & Analytics | Monthly payout cycle with historical record retention | P0 | 2 | Backend | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Teacher Payout Engine | Squad E - Billing & Analytics | Monthly payout statement email dispatch to teachers | P1 | 1 | Backend | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Teacher Payout Engine | Squad E - Billing & Analytics | Student no-show handling (waiting amount added to teacher payout, session carried forward) | P0 | 2 | Backend | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Teacher Payout Engine | Squad E - Billing & Analytics | Teacher no-show handling (admin notification, penalty/deduction, session carried forward) | P0 | 3 | Backend | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Analytics, AI Reports & BI Dashboard | Squad E - Billing & Analytics | Student analytics (attendance, participation, quiz attempts, whiteboard interaction, engagement scores) | P1 | 4 | Backend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Analytics, AI Reports & BI Dashboard | Squad E - Billing & Analytics | AI performance reports (progress insights, talk-time analysis, camera attentiveness) | P1 | 4 | Backend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Analytics, AI Reports & BI Dashboard | Squad E - Billing & Analytics | Session completion analytics | P1 | 1 | Backend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Analytics, AI Reports & BI Dashboard | Squad E - Billing & Analytics | Admin BI dashboard (revenue, enrollments, conversion/renewal/refund, utilization, occupancy, course revenue) | P1 | 3 | Full-Stack | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Analytics, AI Reports & BI Dashboard | Squad E - Billing & Analytics | CSV exports (attendance, revenue, payout, conversion reports) | P1 | 2 | Backend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Analytics, AI Reports & BI Dashboard | Squad E - Billing & Analytics | Bulk email to active students / per-batch | P1 | 2 | Backend | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
QA / Release - Discovery | Squad F - QA / DevOps / Release | Test strategy & environments | P0 | 2 | QA | Sprint 0 | 2026-07-13 | 2026-07-26 | Done
QA / Release - Discovery | Squad F - QA / DevOps / Release | White-label branding requirements gathering | P1 | 1 | PM/BA | Sprint 0 | 2026-07-13 | 2026-07-26 | Blocked
QA / Release - Discovery | Squad F - QA / DevOps / Release | Documentation templates & UAT plan skeleton | P0 | 1 | PM/BA | Sprint 0 | 2026-07-13 | 2026-07-26 | Done
Test Automation Setup | Squad F - QA / DevOps / Release | CI pipeline test integration | P0 | 2 | QA | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Test Automation Setup | Squad F - QA / DevOps / Release | Smoke-test suite for Sprint 1 deliverables | P0 | 2 | QA | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Test Automation Setup | Squad F - QA / DevOps / Release | Security test plan | P0 | 1 | QA | Sprint 1 | 2026-07-27 | 2026-08-09 | Done
Continuous Regression - Wave 1 | Squad F - QA / DevOps / Release | Regression pass on Auth/RBAC and Admin core | P0 | 2 | QA | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Continuous Regression - Wave 1 | Squad F - QA / DevOps / Release | Regression pass on Jitsi live classroom integration | P0 | 2 | QA | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Continuous Regression - Wave 1 | Squad F - QA / DevOps / Release | Security testing kick-off (RBAC & payment data access) | P0 | 2 | QA | Sprint 2 | 2026-08-10 | 2026-08-23 | Not Started
Continuous Regression - Wave 2 + Load Test Prep | Squad F - QA / DevOps / Release | Regression on Whiteboard, Scheduling, Teacher/Admission portals | P0 | 3 | QA | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Continuous Regression - Wave 2 + Load Test Prep | Squad F - QA / DevOps / Release | Live-classroom concurrency load-test scripting | P0 | 2 | QA | Sprint 3 | 2026-08-24 | 2026-09-06 | Not Started
Continuous Regression - Wave 3 | Squad F - QA / DevOps / Release | Regression on Billing/Payout/Analytics | P0 | 3 | QA | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Continuous Regression - Wave 3 | Squad F - QA / DevOps / Release | Full technical & API documentation drafting begins | P0 | 3 | PM/BA | Sprint 4 | 2026-09-07 | 2026-09-20 | Not Started
Cross-Squad Integration Hardening | A/B/C/D/E | End-to-end integration pass across all portals + Jitsi live classroom | P0 | 4 | Full Team | Sprint 5 | 2026-09-21 | 2026-10-04 | Not Started
Cross-Squad Integration Hardening | A/B/C/D/E | Fix cross-module defects surfaced by regression | P0 | 4 | Full Team | Sprint 5 | 2026-09-21 | 2026-10-04 | Not Started
Cross-Squad Integration Hardening | A/B/C/D/E | Full technical documentation finalization | P0 | 2 | PM/BA | Sprint 5 | 2026-09-21 | 2026-10-04 | Not Started
Cross-Squad Integration Hardening | A/B/C/D/E | API documentation finalization | P0 | 2 | Backend | Sprint 5 | 2026-09-21 | 2026-10-04 | Not Started
Cross-Squad Integration Hardening | A/B/C/D/E | Admin guide / user manual | P0 | 2 | PM/BA | Sprint 5 | 2026-09-21 | 2026-10-04 | Not Started
Cross-Squad Integration Hardening | A/B/C/D/E | Source code, repository, cloud & API ownership transfer packaging | P0 | 1 | DevOps | Sprint 5 | 2026-09-21 | 2026-10-04 | Not Started
Full Regression + Load + Security Testing | Squad F - QA / DevOps / Release | End-to-end regression testing (all 6 portals) | P0 | 4 | QA | Sprint 5 | 2026-09-21 | 2026-10-04 | Not Started
Full Regression + Load + Security Testing | Squad F - QA / DevOps / Release | Load/performance testing (live classroom concurrency) | P0 | 3 | QA | Sprint 5 | 2026-09-21 | 2026-10-04 | Not Started
Full Regression + Load + Security Testing | Squad F - QA / DevOps / Release | Security testing (RBAC, payment data, session access) | P0 | 3 | QA | Sprint 5 | 2026-09-21 | 2026-10-04 | Not Started
Full Regression + Load + Security Testing | Squad F - QA / DevOps / Release | Bug triage & fixes | P0 | 3 | Full-Stack | Sprint 5 | 2026-09-21 | 2026-10-04 | Not Started
UAT, Deployment & Go-Live | Squad F - QA / DevOps / Release | Operational readiness sign-off (role-wise access, academic ops, billing ops, reporting readiness checklist) | P0 | 1 | PM/BA | Stabilization Week | 2026-10-05 | 2026-10-11 | Not Started
UAT, Deployment & Go-Live | Squad F - QA / DevOps / Release | UAT with client stakeholders | P0 | 3 | PM/BA | Stabilization Week | 2026-10-05 | 2026-10-11 | Not Started
UAT, Deployment & Go-Live | Squad F - QA / DevOps / Release | UAT feedback fixes | P0 | 2 | Full-Stack | Stabilization Week | 2026-10-05 | 2026-10-11 | Not Started
UAT, Deployment & Go-Live | Squad F - QA / DevOps / Release | Production deployment | P0 | 1 | DevOps | Stabilization Week | 2026-10-05 | 2026-10-11 | Not Started
UAT, Deployment & Go-Live | Squad F - QA / DevOps / Release | Admin training sessions | P1 | 1 | PM/BA | Stabilization Week | 2026-10-05 | 2026-10-11 | Not Started
UAT, Deployment & Go-Live | Squad F - QA / DevOps / Release | Go-live support & hypercare kickoff | P0 | 2 | Full Team | Stabilization Week | 2026-10-05 | 2026-10-11 | Not Started

## Assumptions & Legend
Item | Detail
Project Start Date | Monday, 13 July 2026
Target Completion | Go-live by Sunday, 11 October 2026 (13 weeks / ~3 calendar months)
Sprint Length | 2 weeks (6 sprints: Sprint 0-5) + 1-week Stabilization/Go-Live week
Team Composition Assumed | ~26-30 people across 6 parallel squads (roughly 4-5 each: 2-3 developers + shared QA/DevOps/PM support): Squad A Platform/Core, Squad B Live Classroom & Whiteboard, Squad C Academic Ops (Scheduling/Teacher/Admission), Squad D Parent & Content, Squad E Billing & Analytics, Squad F QA/DevOps/Release (cross-cutting, active from Sprint 1 onward).
Scope | Full WBS scope EXCLUDING the Parent Mobile App (iOS/Android), which is deferred to a future phase per client decision. All web portals (Admin, Sub Admin, Admission, Teacher, Parent), Live Classroom + Whiteboard + Gamification, Scheduling, Billing + Dual Payment Gateway + Fee Suspension + Teacher Payout, Analytics/AI/BI, and White-label/Handover are in scope.
Video/Audio Decision | Jitsi Meet (client-provided) integrated via IFrame API / SDK rather than custom-built WebRTC. This is what makes the Live Classroom Engine achievable within Sprint 1 instead of requiring 6+ weeks for a ground-up build. Whiteboard is a separate layer built on top of the Jitsi session.
Why This Is Aggressive | Compressing ~13 months of lean-team work into 3 months required (a) buying Jitsi instead of building video/audio, (b) running 6 squads in parallel instead of one team working module-by-module, and (c) folding QA into every sprint instead of a dedicated hardening phase at the end. This trades cost (much larger team) for speed and carries real integration risk across squads working concurrently on shared data models.
Biggest Delivery Risks | (1) Cross-squad dependency collisions in Sprint 1 (Auth/RBAC, Scheduling, Billing, Jitsi all being built simultaneously against a shared schema) - mitigated by finishing the DB schema and API contracts in Sprint 0. (2) Jitsi customization limits for teacher controls (per-student mute, waiting room) may need moderation-API workarounds. (3) Only 1 stabilization week for UAT + fixes + go-live is thin for a platform this size; treat Sprint 5 defect count as the go/no-go signal.
Deferred / Phase 2 | Parent Mobile App (iOS/Android). Recommend scoping and quoting this separately once the web platform is live and stable.
Priority Key | P0 = Must-have for go-live ¦ P1 = Important, can trail by 1 sprint if needed ¦ P2 = Nice-to-have / first to descope under time pressure
Status Key | Not Started ¦ In Progress ¦ Blocked ¦ Done (update as sprints execute)
Open Item | Parent enrollment form field list to be supplied by client before Sprint 2 (Content Access Control + Parent Enrollment) begins - flagged as a blocking dependency in the Sprint 0 backlog.
Source Documents | SOFTWARE REQUIREMENT FOR THE READER NEST.docx and Reader_Nest_LMS.pdf (WBS text + the 10 image-only 'Application Flow' diagram pages, rendered and reviewed directly since they don't extract as text).
Gap-Fill Review (this revision) | Re-analyzed both source documents including the flow diagrams and added items that were implied by the diagrams/requirements but missing from the task list: (1) Scheduling conflict / teacher availability check, (2) Reschedule/cancel session functionality, (3) Auto-assign teacher to demo sessions, (4) Course completion tracking + automatic batch-to-dormant transition, (5) Refund request tracking workflow, (6) Renewal tracking workflow, (7) Monthly payout statement email dispatch to teachers, (8) Corrected no-show logic to reflect that carry-forward triggers independently per party (teacher no-show -> admin notification + penalty; student no-show -> waiting amount added to payout) rather than requiring both to no-show, (9) Named 'Academic Coordinator' and 'Management' role presets (both called out as distinct personas in the PDF but not previously instantiated as configured roles), (10) Long-duration session verification for Jitsi, (11) Operational readiness sign-off checklist before go-live.
Gap-Fill Review (Sprint 0 execution, 2026-07-10) | Second reconciliation of Software.pdf + Reader_Nest_LMS.pdf against the backlog before Sprint 0 build start. Added 5 missing tasks: (1) Auto-send login credentials email on admin-created accounts (Software.pdf 'Parent Self-Enrollment' - Sprint 1, Squad A); (2) Teacher session resource upload (Teacher Portal WBS 'Resource upload' - Sprint 1, Squad C); (3) Teacher attendance capture, login/join-based (WBS Attendance Automation - Sprint 2, Squad C; was in sprint deliverable text but had no backlog row); (4) Remote access grant control (Software.pdf teacher controls 'Give remote access' - Sprint 2, Squad B, P2); (5) Tutor notes creation & management teacher-side (Teacher WBS 'Records' - Sprint 3, Squad C; backlog previously only covered admin viewing of tutor notes in Sprint 4).
Sprint 0 & 1 Status Pass (2026-07-10) | Sprint 0 and Sprint 1 backlogs fully executed and statuses updated to reflect real progress. Done: all discovery docs (Jitsi architecture, whiteboard evaluation, KPI list, workflow mapping, test strategy, UAT plan, security test plan), CI/CD pipelines (backend + frontend GitHub Actions), design system (existing shadcn/ui library), full 6-portal UX (existing React app), backend Sprint 1 (auth/RBAC/JWT, user CRUD + credential email, courses/batches, automated scheduling, course-completion -> dormant transition, resource upload/download with access grants, demo bookings, billing core with dual payment-account routing, invoices/receipts/payments), 10-test xUnit smoke suite, and Jitsi IFrame API live-classroom embed (native video/audio/screen-share/chat/reactions/raise-hand). In Progress: permission-matrix admin UI (backend ready, sub-admin ids need to move from mock to real accounts), teacher moderation controls (mute/waiting-room UI on top of native Jitsi toolbar), recurring/auto-billing scheduler, gateway SDK wiring (accounts modeled and routed, no live credentials yet). Blocked on client: requirement sign-off meeting, client-owned Git/cloud accounts, payment gateway account credentials, white-label branding assets, and the enrollment form field list. Not Started: session summaries/history surface, Jibri-based cloud recording (needs the client cloud account first).